PDFFLOW

ENGINEERING EXECUTION HANDBOOK

From Day 1 to Production Launch

Tech Lead:  Santanu

Backend: Gyan  |  Frontend: Archita, Harshitha

Research: Parv, Samriddhi  |  Content: Arpit

Interns: Backend · Frontend · DevOps · QA

Version 1.0

CONFIDENTIAL — FOR INTERNAL USE ONLY

# TABLE OF CONTENTS

# SECTION 1 — PROJECT OVERVIEW

## 1.1  What Is PDFFlow?

PDFFlow is a modern, web-based Software-as-a-Service (SaaS) platform that provides powerful PDF manipulation, conversion, and AI-powered intelligence tools to individuals, small businesses, and enterprises — all through a clean browser interface with no software installation required.

Think of PDFFlow as the professional, privacy-respecting alternative to tools like ILovePDF, Smallpdf, and Adobe Acrobat Online — but faster, smarter, and built with developer-grade architecture that scales to millions of users.

### Core Capabilities

- Merge, split, compress, rotate, and reorder PDF pages

- Convert PDFs to and from Word, Excel, PowerPoint, JPG, and more

- Add page numbers, watermarks, and digital signatures

- Protect PDFs with passwords and unlock password-locked PDFs

- Run OCR (Optical Character Recognition) to make scanned PDFs searchable

- Use AI to summarise, translate, and rewrite PDF content

## 1.2  Why Are We Building PDFFlow?

PDF tools are universally needed but universally painful. Existing solutions have one or more of these problems:

- They are slow and rely on heavy desktop applications

- Free tiers are heavily restricted with paywalls on basic features

- Privacy is poor — files are stored on third-party servers without explicit consent

- They lack AI-powered intelligence for document understanding

- Developer APIs are expensive and poorly documented

PDFFlow solves all of these by offering:

- Fast, asynchronous background processing via Celery + Redis

- Transparent file handling — files are purged within 60 minutes unless the user saves them

- A freemium model that gives real value on the free tier

- First-class AI features powered by Claude/OpenAI APIs

- A public developer API for programmatic access

## 1.3  Product Vision

"PDFFlow will be the document intelligence platform that every professional, student, and business keeps open in their browser — a tool as familiar as Gmail and as powerful as Adobe Acrobat."

We are building toward:

- A web application with 20+ PDF tools available in one unified interface

- An AI layer that understands document context, not just bytes

- A public REST API enabling developers to integrate PDFFlow into their apps

- A B2B white-label offering for enterprises and educational institutions

- Mobile apps (Phase 3) extending access to Android and iOS

## 1.4  Business Vision

| Horizon | Goal |
| --- | --- |
| 6 Months | Public beta with 10 core tools live, 500 registered users, stable CI/CD pipeline |
| 12 Months | 20 tools live, 5,000 users, freemium revenue model active, developer API released |
| 18 Months | 50,000 users, B2B partnerships initiated, mobile apps in development |
| 24 Months | 100,000+ users, enterprise white-label offering, Series A positioning |

## 1.5  Long-Term Roadmap

### Phase 1 — Foundation (Months 1–3)

- Architecture finalized and repositories created

- Development environment standardized across all team members

- 10 core PDF tools built, tested, and deployed to staging

- Authentication, file upload, and job queue systems live

- CI/CD pipeline running on GitHub Actions

### Phase 2 — Growth (Months 4–6)

- Remaining 10 tools (including AI features) built and deployed

- Public beta launch with real user feedback incorporated

- Performance benchmarks hit: <3s processing for files under 10 MB

- Developer API v1 documented and released

- Monitoring, alerting, and on-call procedures established

### Phase 3 — Scale (Months 7–12)

- Infrastructure auto-scaling for traffic spikes

- Mobile applications (React Native) developed

- B2B / enterprise white-label version shipped

- Advanced AI features: multi-document comparison, contract analysis

- Team scaling from 11 to 20+ members

## 1.6  Expected Final Product

At full completion, PDFFlow will be a production-grade web application with:

- A polished Next.js frontend with responsive design (desktop + mobile)

- A FastAPI Python backend handling concurrent file-processing jobs

- A Celery + Redis worker cluster for asynchronous task execution

- PostgreSQL as the primary relational database

- AWS S3 / Cloudflare R2 for file storage with automatic expiry

- Nginx as the reverse proxy with SSL termination

- Prometheus + Grafana for real-time monitoring and dashboards

- GitHub Actions for automated testing and deployment

- A comprehensive developer API with authentication tokens and rate limiting

- All 20 tools functional, tested, and documented

# SECTION 2 — COMPLETE TEAM STRUCTURE

## 2.1  Team Hierarchy

All roles ultimately report to Santanu as the project's Tech Lead and primary decision-maker. The hierarchy is intentionally flat to keep communication fast, but review and merge permissions follow a strict chain to maintain code quality.

| Role | Name | Reports To | Primary Accountability |
| --- | --- | --- | --- |
| Tech Lead | Santanu | Founder / Stakeholder | Architecture, releases, team unblocking |
| Backend Engineer | Gyan | Santanu | API development, Celery workers, DB |
| Frontend Engineer | Archita | Santanu | Core UI pages, component library |
| Frontend Engineer | Harshitha | Santanu | Integrations, responsiveness, testing |
| Backend Intern | TBD | Gyan → Santanu | Supporting API tasks, unit tests |
| Frontend Intern | TBD | Archita → Santanu | Components, bug fixes, styling |
| DevOps Intern | TBD | Santanu | Docker, CI/CD, monitoring setup |
| QA Intern | TBD | Santanu | Manual + automated testing |
| Researcher | Parv | Santanu | Feature research, UX benchmarking |
| Researcher | Samriddhi | Santanu | Competitor analysis, UI standards |
| Content Lead | Arpit | Santanu | All written content, SEO, docs |

## 2.2  Code Review & Merge Rules

These rules are non-negotiable and enforced via GitHub branch protection settings. Violating them will result in your PR being closed.

| Action | Who Can Do It | Conditions |
| --- | --- | --- |
| Open a PR to develop | Anyone | Branch must be up-to-date with develop |
| Review PRs (Backend) | Gyan, Santanu | At least 1 approval before merge |
| Review PRs (Frontend) | Archita, Harshitha, Santanu | At least 1 approval before merge |
| Merge to develop | Santanu, Gyan (backend), Archita (frontend) | All checks passed, PR approved |
| Merge to main | Santanu only | Only from release/* branch |
| Force push to main or develop | Nobody | Never allowed, ever |
| Deploy to production | Santanu only | After QA sign-off on staging |

## 2.3  Communication Channels

| Channel | Purpose | Response Expectation |
| --- | --- | --- |
| #general (Slack/Discord) | Announcements, standups | Within 2 hours during work hours |
| #backend | Backend technical discussions | Within 4 hours |
| #frontend | Frontend technical discussions | Within 4 hours |
| #devops | Deployment, infra alerts | Within 30 minutes for incidents |
| GitHub Issues | Bug reports, feature tasks | Acknowledge within 24 hours |
| GitHub PRs | Code review | First review within 24 hours |

# SECTION 3 — COMPLETE DEVELOPMENT ENVIRONMENT SETUP

Every team member must complete this setup before writing a single line of code. If anything fails, stop and ask Santanu before proceeding. A broken local environment will waste hours of your time later.

## 3.1  Required Software (All Roles)

| Software | Version | Install Command / URL |
| --- | --- | --- |
| Git | Latest | https://git-scm.com/downloads |
| Node.js | 20.x LTS | https://nodejs.org or nvm install 20 |
| Python | 3.11+ | https://python.org or pyenv install 3.11 |
| Docker Desktop | Latest | https://www.docker.com/products/docker-desktop |
| VS Code | Latest | https://code.visualstudio.com |
| Postman | Latest | https://postman.com/downloads |

## 3.2  Required VS Code Extensions

- Python (ms-python.python) — Python IntelliSense and debugger

- Pylance (ms-python.vscode-pylance) — fast Python type checking

- ESLint (dbaeumer.vscode-eslint) — JavaScript/TypeScript linting

- Prettier (esbenp.prettier-vscode) — code formatting

- Tailwind CSS IntelliSense (bradlc.vscode-tailwindcss) — class suggestions

- GitLens (eamodio.gitlens) — enhanced Git history in VS Code

- Docker (ms-azuretools.vscode-docker) — Dockerfile and Compose support

- Thunder Client (rangav.vscode-thunder-client) — lightweight API testing

- REST Client (humao.rest-client) — test APIs from .http files

- Error Lens (usernamehere.errorlens) — inline error display

## 3.3  Repository Access & Clone

After receiving your GitHub invitation from Santanu, clone the repositories:

# Main application repository

git clone https://github.com/pdfflow/pdfflow-app.git

# Infrastructure / DevOps repository

git clone https://github.com/pdfflow/pdfflow-infra.git

# Documentation repository

git clone https://github.com/pdfflow/pdfflow-docs.git

## 3.4  Backend Environment Setup (Gyan, Backend Intern, Santanu)

- Navigate to the backend directory

cd pdfflow-app/backend

- Create and activate a virtual environment

python -m venv venv

source venv/bin/activate          # macOS / Linux

venv\Scripts\activate             # Windows

- Install all Python dependencies

pip install -r requirements.txt

pip install -r requirements-dev.txt

- Copy the environment template and fill in values

cp .env.example .env

# Edit .env with your local database URL, Redis URL, API keys

- Start the full local stack with Docker Compose

docker compose up -d postgres redis

- Run database migrations

alembic upgrade head

- Start the FastAPI development server

uvicorn app.main:app --reload --host 0.0.0.0 --port 8000

- Verify the server is running

open http://localhost:8000/docs   # Swagger UI

open http://localhost:8000/health  # Health check

## 3.5  Frontend Environment Setup (Archita, Harshitha, Frontend Intern)

- Navigate to the frontend directory

cd pdfflow-app/frontend

- Install Node.js dependencies

npm install

- Copy environment template

cp .env.local.example .env.local

# Set NEXT_PUBLIC_API_URL=http://localhost:8000

- Start the Next.js development server

npm run dev

- Verify the frontend is running

open http://localhost:3000

## 3.6  DevOps Environment Setup (DevOps Intern)

- Install Docker Desktop and verify

docker --version && docker compose version

- Start the full stack

cd pdfflow-app

docker compose up --build

- Verify all services

docker compose ps

# All services should show 'running'

- Access service dashboards

http://localhost:8000/docs      # FastAPI

http://localhost:3000          # Next.js

http://localhost:5555          # Flower (Celery monitor)

http://localhost:9090          # Prometheus

http://localhost:3001          # Grafana

## 3.7  Required Environment Variables

| Variable | Required By | Description |
| --- | --- | --- |
| DATABASE_URL | Backend | PostgreSQL connection string |
| REDIS_URL | Backend/Workers | Redis connection string |
| SECRET_KEY | Backend | JWT signing secret (32+ chars) |
| AWS_ACCESS_KEY_ID | Backend | S3 storage access key |
| AWS_SECRET_ACCESS_KEY | Backend | S3 storage secret |
| S3_BUCKET_NAME | Backend | File storage bucket name |
| ANTHROPIC_API_KEY | Backend (AI) | Claude API key for AI tools |
| NEXT_PUBLIC_API_URL | Frontend | Backend API base URL |
| SENTRY_DSN | Both | Error tracking DSN |
| MAX_FILE_SIZE_MB | Backend | Max upload size (default: 100) |

# SECTION 4 — DETAILED MEMBER RESPONSIBILITIES

## Santanu — Tech Lead & Backend Engineer

### Mission

Own the entire technical direction of PDFFlow. Design architecture, lead backend engineering, review all code, manage releases, unblock every team member, and ensure the product ships on time at production quality.

### Primary Responsibilities

- Define and maintain the system architecture (API design, database schema, microservice boundaries)

- Set up and maintain all GitHub repositories, branch protection rules, and CI/CD pipelines

- Lead development of the most complex backend modules (file processing engine, auth system)

- Review and approve all PRs that touch core backend logic, DevOps configs, or database migrations

- Conduct weekly sprint planning and daily standups

- Make all final deployment decisions to production

- Mentor Gyan, Backend Intern, DevOps Intern, and QA Intern

### Secondary Responsibilities

- Write technical documentation and architectural decision records (ADRs)

- Conduct 1:1s with all team members weekly

- Evaluate and approve all third-party library additions

- Respond to production incidents within 15 minutes

### Technologies & Libraries

- FastAPI, SQLAlchemy, Alembic, Celery, Redis, PostgreSQL

- Docker, Docker Compose, GitHub Actions, Nginx

- Prometheus, Grafana, Sentry

- PyMuPDF (fitz), pypdf, pdf2image, Pillow

- Anthropic Claude API, OpenAI API

- AWS S3 / Cloudflare R2

### Folder & File Ownership

- backend/ (entire directory)

- docker-compose.yml, docker-compose.prod.yml

- .github/workflows/*.yml

- alembic/ (all migrations)

- docs/architecture/ (all ADRs)

### Git Branches

- Creates feature/backend/* branches for his own development

- Creates release/* branches for deployments

- Creates hotfix/* branches for production emergency fixes

- The only person who merges to main

### Success Metrics

- Zero critical bugs escaping to production per sprint

- All PRs reviewed within 24 hours

- Deployment success rate >99%

- Team velocity improving sprint-over-sprint

- All 20 tools shipped by end of Phase 2

### Definition of Done

- Feature is code-reviewed, all tests pass, deployed to staging

- QA has signed off on staging

- Documentation has been updated

- Monitoring alerts configured for the new feature

- Production deployment completed without rollback

## Gyan — Backend Engineer

### Mission

Build, test, and maintain all PDF-processing API endpoints and Celery workers. Take ownership of the file transformation pipeline and ensure every tool works reliably, securely, and at scale.

### Primary Responsibilities

- Implement all 20 PDF tool APIs as FastAPI endpoints under /api/v1/tools/

- Write and maintain all Celery workers that perform the actual PDF processing

- Design and implement database models for jobs, files, users, and usage tracking

- Write unit tests (pytest) for every API endpoint and worker

- Optimize processing performance — target <3 seconds for files under 10MB

- Implement file upload, download, and S3 integration

- Integrate AI APIs (Anthropic Claude) for summarise, translate, and rewrite features

### Secondary Responsibilities

- Review Backend Intern's PRs and provide detailed feedback

- Write integration tests for multi-step workflows

- Create and maintain Postman collections for the API

- Document all API endpoints in OpenAPI/Swagger format

### Technologies & Libraries

- FastAPI, Pydantic v2, SQLAlchemy 2.0, Alembic

- Celery 5.x, Redis (via redis-py)

- PyMuPDF (fitz), pypdf, pdf2image, Pillow

- LibreOffice (headless) for office-to-PDF conversions

- pytesseract + Tesseract OCR for OCR processing

- boto3 for AWS S3 interactions

- Anthropic SDK / OpenAI SDK for AI features

- pytest, httpx (for async test client), factory-boy (test data)

### Folder & File Ownership

- backend/app/api/v1/endpoints/ — all tool API endpoints

- backend/app/workers/ — all Celery task files

- backend/app/models/ — SQLAlchemy models

- backend/app/schemas/ — Pydantic request/response schemas

- backend/app/services/ — business logic services

- backend/tests/ — all test files

### Git Branches

- feature/backend/<tool-name> — one branch per feature

- bugfix/backend/<issue-number>-<short-description>

- Examples: feature/backend/merge-pdf, feature/backend/ocr-tool

### Success Metrics

- All 20 tools have working API endpoints and passing tests

- Processing time <3s for files under 10MB on 95th percentile

- Test coverage >80% for all backend modules

- Zero data loss incidents in file handling

### Definition of Done

- API endpoint returns correct response with valid PDF input

- Unit tests written and all passing (pytest -v)

- Edge cases handled (corrupted file, empty file, oversized file)

- Endpoint documented in OpenAPI schema

- PR approved by Santanu and merged to develop

## Archita — Frontend Engineer — Core UI

### Mission

Build the primary user interface of PDFFlow. Own the component library, all tool pages, and the core user experience. Your code is what users see and touch — make it fast, accessible, and delightful.

### Primary Responsibilities

- Build and maintain the shared UI component library (buttons, modals, file upload, progress bars)

- Create all 20 tool pages following the established design system

- Implement file drag-and-drop upload with progress indicators

- Build the dashboard and job history pages

- Implement the authentication UI (login, signup, forgot password)

- Ensure all components are accessible (WCAG 2.1 AA compliant)

- Maintain Storybook documentation for all shared components

### Secondary Responsibilities

- Review Frontend Intern's PRs and provide constructive feedback

- Coordinate with Harshitha to ensure consistent styling across their respective areas

- Write Jest unit tests for all shared components

- Participate in Parv and Samriddhi's UX research sessions

### Technologies & Libraries

- Next.js 14 (App Router), React 18, TypeScript

- Tailwind CSS, Shadcn/ui, Radix UI primitives

- Zustand (global state), React Query / TanStack Query (server state)

- React Hook Form + Zod (form handling and validation)

- Framer Motion (animations), React Dropzone (file uploads)

- Jest + React Testing Library (unit/component tests)

- Storybook (component documentation)

### Folder & File Ownership

- frontend/app/(tools)/ — all tool pages

- frontend/app/(auth)/ — authentication pages

- frontend/components/ui/ — design system components

- frontend/components/tools/ — tool-specific components

- frontend/hooks/ — shared custom React hooks

- frontend/lib/ — utility functions and constants

- frontend/stories/ — Storybook files

### Git Branches

- feature/frontend/<component-or-page> — one branch per feature

- Examples: feature/frontend/merge-pdf-page, feature/frontend/file-upload-component

- bugfix/frontend/<issue-number>-<description>

### Success Metrics

- All 20 tool pages are functional and passing QA

- Lighthouse performance score >85 on all tool pages

- All components have Storybook entries

- Zero accessibility errors on automated audit

### Definition of Done

- Component renders correctly across Chrome, Firefox, Safari

- Jest tests written and passing

- Storybook story created for shared components

- Reviewed and approved by Harshitha or Santanu

- Merged to develop branch

## Harshitha — Frontend Engineer — Integrations & Quality

### Mission

Own the integration layer between the frontend and backend APIs. Ensure all tool pages communicate correctly with the server, handle all error states gracefully, and that the product is fully responsive across all device sizes.

### Primary Responsibilities

- Implement all frontend-to-backend API calls using React Query / Axios

- Build file polling mechanism (check job status every 2 seconds until complete)

- Handle all error states — network failures, server errors, file type validation

- Own full mobile responsiveness for all pages (320px to 1440px)

- Implement loading skeletons and progressive enhancement

- Build the settings and account management pages

- Integrate third-party services (analytics, error tracking with Sentry)

### Secondary Responsibilities

- Write Playwright E2E tests for all critical user journeys

- Coordinate with QA Intern on test automation

- Help Archita with styling consistency

- Performance optimization (lazy loading, code splitting)

### Technologies & Libraries

- Next.js 14, React 18, TypeScript

- Axios / Fetch API for HTTP requests

- React Query for server state management and polling

- Playwright for E2E tests

- Tailwind CSS for responsive styling

- Sentry SDK for frontend error tracking

### Folder & File Ownership

- frontend/app/(account)/ — account and settings pages

- frontend/lib/api/ — all API client functions

- frontend/lib/hooks/api/ — React Query hooks for each tool

- frontend/tests/e2e/ — Playwright test files

- frontend/components/layout/ — navigation, header, footer

### Git Branches

- feature/frontend/api-<tool-name> — API integration branches

- feature/frontend/responsive-<page-name> — responsiveness branches

- e2e/<workflow-name> — E2E test branches

### Success Metrics

- All E2E tests passing in CI pipeline

- Zero layout breakages below 768px viewport

- API error handling covers all HTTP error codes

- Job polling reliably updates UI within 3 seconds of job completion

### Definition of Done

- API integration tested with real backend on staging

- Error states handled and visible to user

- Mobile responsive at 320px, 768px, 1024px, 1440px breakpoints

- E2E test written for the workflow

- PR approved and merged to develop

# SECTION 5 — SANTANU: COMPLETE ROADMAP (Day 1 to Launch)

## 5.1  Week 1 — Architecture & Repository Setup

- Create GitHub organisation: github.com/pdfflow

- Create three repositories: pdfflow-app, pdfflow-infra, pdfflow-docs

- Set up branch protection rules on main and develop for all repos

- Create the project board in GitHub Projects with columns: Backlog, In Progress, In Review, Done

- Write the Architecture Decision Record (ADR-001): Technology Stack Selection

- Define folder structure for both backend/ and frontend/ directories

- Create .env.example files for backend and frontend

- Set up the initial Docker Compose file with all required services

- Invite all team members to GitHub organisation with appropriate roles

- Schedule and run the project kickoff meeting — walk through this handbook

## 5.2  Week 2 — Backend Foundation

- Create FastAPI application skeleton with proper project structure

- Configure SQLAlchemy with PostgreSQL and create initial Alembic migration

- Implement User model: id, email, hashed_password, plan_type, created_at

- Implement Job model: id, user_id, tool_name, status, input_file_key, output_file_key, created_at, completed_at

- Implement authentication endpoints: POST /auth/register, POST /auth/login, POST /auth/refresh

- Set up JWT token generation and validation middleware

- Implement file upload endpoint: POST /files/upload with S3 integration

- Write unit tests for auth and file upload endpoints

- Deploy backend skeleton to staging environment

## 5.3  Week 3-4 — Core Tool Development

- Implement Celery worker infrastructure with Redis broker

- Create base task class with status updates, error handling, and retries

- Build and test first three tools: Merge PDF, Split PDF, Compress PDF

- Implement job status polling endpoint: GET /jobs/{job_id}/status

- Implement file download endpoint: GET /jobs/{job_id}/download

- Review Gyan's first PRs and provide detailed feedback

- Begin architecture review of frontend structure with Archita

## 5.4  Month 2 — Team Leadership & Scale

- Run weekly sprint planning every Monday (30 minutes max)

- Review all architecture decisions before Gyan and interns implement them

- Set up Prometheus metrics collection and Grafana dashboards

- Implement rate limiting middleware (100 requests/hour free, 1000/hour paid)

- Set up Sentry for error tracking in both backend and frontend

- Write ADR-002: File Storage Strategy (S3 vs Cloudflare R2)

- Create and maintain CHANGELOG.md — updated with every release

- Set up GitHub Actions workflow for automated testing

## 5.5  Month 3 — Integration & Quality

- Lead integration sprint: frontend and backend connected end-to-end

- Run load testing with Locust — simulate 100 concurrent users

- Fix all performance bottlenecks identified in load tests

- Coordinate QA Intern's first full regression test cycle

- Prepare and execute staging deployment with full team

- Create deployment runbook: step-by-step production deployment guide

## 5.6  Production Launch Checklist

- All 20 tools functional and tested on staging

- Load testing passed: 100 concurrent users with <3s 95th percentile latency

- Security audit completed: OWASP Top 10 checked

- SSL certificates configured and auto-renewing

- Database backups automated and tested (restore drill done)

- Monitoring alerts configured for: high CPU, high error rate, job queue depth

- On-call rotation defined (Santanu primary, Gyan secondary)

- Rollback procedure documented and tested

- Marketing team notified of launch date

- DNS updated and CDN configured

# SECTION 6 — GYAN: COMPLETE ROADMAP

## 6.1  Week 1 — Onboarding & Setup

- Complete full dev environment setup from Section 3.4

- Clone the pdfflow-app repository and verify local stack runs

- Read the FastAPI documentation: https://fastapi.tiangolo.com

- Read the Celery documentation: https://docs.celeryq.dev

- Pair with Santanu for 2 hours — walk through the existing code

- Pick up your first task from the GitHub Projects board

## 6.2  Backend Modules to Build (In Order)

| Order | Module / File | What It Does | Library |
| --- | --- | --- | --- |
| 1 | workers/merge.py | Merge 2+ PDFs into one file | PyMuPDF |
| 2 | workers/split.py | Split PDF by page range or every N pages | PyMuPDF |
| 3 | workers/compress.py | Reduce file size via compression settings | pypdf, Ghostscript |
| 4 | workers/rotate.py | Rotate pages by 90/180/270 degrees | PyMuPDF |
| 5 | workers/pdf_to_jpg.py | Convert each PDF page to JPG/PNG | pdf2image, Pillow |
| 6 | workers/jpg_to_pdf.py | Combine images into a single PDF | PyMuPDF, Pillow |
| 7 | workers/add_page_numbers.py | Stamp page numbers on each page | PyMuPDF |
| 8 | workers/watermark.py | Add text or image watermark to all pages | PyMuPDF |
| 9 | workers/protect.py | Add password protection to PDF | pypdf |
| 10 | workers/unlock.py | Remove password from PDF | pypdf, qpdf |
| 11 | workers/word_to_pdf.py | Convert .docx to PDF via LibreOffice | LibreOffice CLI |
| 12 | workers/pdf_to_word.py | Convert PDF to editable .docx | python-docx, PyMuPDF |
| 13 | workers/excel_to_pdf.py | Convert .xlsx to PDF via LibreOffice | LibreOffice CLI |
| 14 | workers/pdf_to_excel.py | Extract tables to .xlsx | camelot-py, openpyxl |
| 15 | workers/ppt_to_pdf.py | Convert .pptx to PDF | LibreOffice CLI |
| 16 | workers/ocr.py | Run OCR on scanned/image PDFs | pytesseract, pdf2image |
| 17 | workers/sign.py | Add digital signature to PDF | pyhanko |
| 18 | workers/ai_summarise.py | Extract and summarise document content | Anthropic SDK |
| 19 | workers/ai_translate.py | Translate PDF content to target language | Anthropic SDK |
| 20 | workers/ai_rewrite.py | Rewrite PDF content in chosen tone/style | Anthropic SDK |

## 6.3  API Endpoints to Build

Each tool needs two endpoints following this pattern:

POST /api/v1/tools/{tool-name}

Body: { file_key: string, options: object }

Response: { job_id: string, status: 'queued' }

GET  /api/v1/jobs/{job_id}/status

Response: { status: 'queued'|'processing'|'done'|'failed', progress: 0-100 }

GET  /api/v1/jobs/{job_id}/download

Response: 302 redirect to presigned S3 download URL

## 6.4  Database Tables to Create

- users — id, email, hashed_password, plan_type, created_at, updated_at

- jobs — id, user_id, tool_name, status, input_file_key, output_file_key, error_message, created_at, completed_at

- files — id, user_id, s3_key, original_filename, size_bytes, mime_type, expires_at, created_at

- api_tokens — id, user_id, token_hash, name, last_used_at, created_at, revoked

- usage_logs — id, user_id, tool_name, file_size_bytes, processing_time_ms, created_at

## 6.5  Testing Requirements

- Write a pytest test file for every worker: tests/workers/test_<tool>.py

- Test with: valid input, invalid file type, corrupted file, oversized file

- Write integration tests for the complete flow: upload -> queue -> process -> download

- Maintain test coverage above 80% (enforced by CI pipeline)

- Use factory-boy to generate test data, never hardcode test files

# SECTION 7 — ARCHITA: COMPLETE ROADMAP

## 7.1  Week 1 — Setup & Design System

- Complete frontend environment setup from Section 3.5

- Study the Figma designs provided by Research team (Parv/Samriddhi)

- Set up Shadcn/ui components in the Next.js project

- Define design tokens in tailwind.config.ts: colors, fonts, spacing, breakpoints

- Create Storybook environment: npm run storybook

- Build the first 5 shared components and document them in Storybook

## 7.2  Shared Components to Build (In Order)

| Component | Location | Description |
| --- | --- | --- |
| FileUploadZone | components/ui/FileUploadZone.tsx | Drag-and-drop area with file validation |
| ProgressBar | components/ui/ProgressBar.tsx | Animated job progress indicator |
| ToolCard | components/ui/ToolCard.tsx | Tool selection card on homepage |
| Button (variants) | components/ui/Button.tsx | Primary, secondary, ghost, danger variants |
| Modal | components/ui/Modal.tsx | Accessible dialog with backdrop |
| Toast | components/ui/Toast.tsx | Success, error, info notifications |
| FilePreview | components/ui/FilePreview.tsx | PDF page thumbnail preview |
| PageSelector | components/tools/PageSelector.tsx | Visual page range selector for split/merge |
| DownloadButton | components/ui/DownloadButton.tsx | Triggers file download with loading state |
| PlanBadge | components/ui/PlanBadge.tsx | Shows free/pro plan badge |

## 7.3  Pages to Build

| Page | Route | Key Features |
| --- | --- | --- |
| Homepage | / | Tool grid, hero section, feature highlights |
| Tool Page (template) | /tools/[tool-slug] | Upload zone, options, progress, download — reusable for all 20 tools |
| Login | /auth/login | Email/password form with validation |
| Signup | /auth/signup | Registration form, email verification flow |
| Dashboard | /dashboard | Job history, recent files, usage stats |
| Pricing | /pricing | Free vs Pro plan comparison |
| 404 Page | /_not-found | Friendly error page with navigation |
| Maintenance | /maintenance | Shown during deployments |

## 7.4  State Management Architecture

- Global State (Zustand): authenticated user, file upload queue, active tool

- Server State (React Query): job status polling, user data, job history

- Local State (useState): form inputs, modal open/close, accordion state

- URL State (Next.js search params): active tab, page number for pagination

## 7.5  Definition of Done — Archita

- Component renders without console errors in development

- Component is responsive at all 4 breakpoints (320px, 768px, 1024px, 1440px)

- Jest test written covering happy path and error state

- Storybook story created with all variants shown

- Reviewed and approved by Santanu or Harshitha

# SECTION 8 — HARSHITHA: COMPLETE ROADMAP

## 8.1  Week 1 — Setup & API Layer

- Complete frontend environment setup from Section 3.5

- Study the backend API documentation at localhost:8000/docs

- Create frontend/lib/api/client.ts — configure Axios instance with base URL, auth headers, and interceptors

- Create frontend/lib/api/types.ts — TypeScript interfaces matching all API response schemas

- Pair with Gyan for 2 hours to understand job polling patterns

## 8.2  API Integration Modules to Build

| Module | File | Responsibility |
| --- | --- | --- |
| Auth API | lib/api/auth.ts | login(), register(), refreshToken(), logout() |
| File Upload API | lib/api/files.ts | uploadFile() with multipart/form-data |
| Tool API | lib/api/tools.ts | submitJob(tool, fileKey, options) |
| Job Polling Hook | hooks/api/useJobStatus.ts | React Query hook polling every 2s until done |
| Download Handler | lib/api/download.ts | getDownloadUrl(jobId), triggerDownload() |
| User API | lib/api/user.ts | getProfile(), updateProfile(), getUsage() |
| Jobs History API | lib/api/jobs.ts | listJobs(), getJob(), deleteJob() |

## 8.3  Responsiveness Requirements

- 320px (iPhone SE) — tool still fully usable, no horizontal scroll

- 375px (iPhone 14) — default mobile breakpoint, most users

- 768px (iPad) — two-column layout where appropriate

- 1024px (iPad Pro / small laptop) — full layout visible

- 1440px (desktop) — maximum content width, centered

## 8.4  Playwright E2E Tests to Write

- tests/e2e/auth.spec.ts — Register, login, logout, protected route redirect

- tests/e2e/merge-pdf.spec.ts — Upload 2 PDFs, click Merge, wait for download

- tests/e2e/compress-pdf.spec.ts — Upload PDF, compress, verify output is smaller

- tests/e2e/upload-validation.spec.ts — Upload wrong file type, verify error message

- tests/e2e/job-history.spec.ts — Complete a job, verify it appears in dashboard

- tests/e2e/mobile.spec.ts — Run critical flows at 375px viewport

## 8.5  Error States to Handle

- Network timeout (>30s): show retry button with countdown

- File too large (>100MB): show error before upload begins

- Wrong file type: show specific error (PDF required, got .docx)

- Job failed on server: show descriptive error from API response

- Session expired: auto-redirect to login with return URL stored

- Server 500: show generic error with support email link

# SECTION 9 — BACKEND INTERN: COMPLETE ROADMAP

Welcome to PDFFlow. This is your complete guide from Day 1 through Week 6. Follow it step by step. If you get stuck, ask Gyan first, then Santanu. Never stay stuck for more than 30 minutes without asking for help.

## 9.1  Week 1 — Environment & Learning

- Complete the full backend environment setup (Section 3.4)

- Read: Python official tutorial (https://docs.python.org/3/tutorial/) — skim, focus on functions, classes, modules

- Read: FastAPI tutorial (https://fastapi.tiangolo.com/tutorial/) — complete the entire first section

- Read: What is REST? (https://restfulapi.net)

- Create a 'Hello World' FastAPI app locally — one route that returns JSON

- Read Gyan's existing code in backend/app/api/v1/endpoints/ — understand the patterns

- Shadow Gyan for 1 hour — watch him build an endpoint from scratch

End of Week 1 checkpoint: You can explain what a REST endpoint is, what JSON is, and how FastAPI handles requests. Share your Hello World app with Gyan.

## 9.2  Week 2 — First Real Task

- Pick up your first GitHub issue labeled 'good-first-issue'

- Create your feature branch: git checkout -b feature/backend/<task-name>

- Write the code following the patterns you observed in Week 1

- Write at least 3 pytest unit tests for your code

- Run the full test suite: pytest -v and ensure nothing is broken

- Open your first Pull Request to the develop branch

- Address all review comments from Gyan within 24 hours

End of Week 2 checkpoint: Your first PR is merged. Gyan gives feedback on code quality.

## 9.3  Week 3 — Databases & Models

- Read: SQLAlchemy documentation — models, relationships, queries

- Read: Alembic documentation — migrations

- Add a new column to an existing model (assigned by Gyan) and create the migration

- Write a database query that filters, joins, and paginates results

- Understand what a Pydantic schema is and why it is separate from the SQLAlchemy model

## 9.4  Week 4 — Celery Workers

- Read: Celery documentation — tasks, chains, error handling

- Trace the full lifecycle of a job: HTTP request -> Celery task -> status update -> result

- Implement a simple Celery task (assigned by Gyan)

- Learn how to monitor Celery tasks in Flower at localhost:5555

- Write a test that mocks the Celery task execution

## 9.5  Week 5 — Assigned Tool Implementation

- Gyan will assign you one tool from the list (typically a simpler one like rotate or watermark)

- Implement the full worker, API endpoint, schema, and tests

- Submit for review — expect 2-3 rounds of review feedback

- Final version merged to develop after approval

## 9.6  Week 6 — Integration & Handoff

- Write integration tests that test your tool end-to-end

- Update the API documentation for your endpoint

- Document any gotchas or edge cases in the team Notion

- Demo your completed tool in the weekly team meeting

# SECTION 10 — FRONTEND INTERN: COMPLETE ROADMAP

## 10.1  Learning Path

### Week 1 — React Fundamentals

- Complete React official tutorial: https://react.dev/learn

- Understand: components, props, state (useState), effects (useEffect)

- Build a Todo app locally to prove understanding

- Read Archita's existing components and identify patterns

### Week 2 — TypeScript & Next.js

- Read: TypeScript in 5 minutes (https://www.typescriptlang.org/docs/handbook/typescript-in-5-minutes.html)

- Read: Next.js App Router documentation https://nextjs.org/docs

- Understand: file-based routing, Server Components vs Client Components, layouts

- Clone the pdfflow frontend and run it locally

### Week 3 — Tailwind CSS

- Read: Tailwind CSS Core Concepts (https://tailwindcss.com/docs)

- Learn the responsive prefix system: sm:, md:, lg:, xl:

- Study how existing pages use Tailwind in the codebase

## 10.2  Assigned Tasks (After Learning Weeks)

- Build the 404 error page component (designed by research team)

- Build the 'Feature Highlights' section on the homepage

- Fix responsive layout issues flagged by QA Intern

- Add loading skeleton to the job history page

- Implement the FAQ accordion component for the pricing page

- Write Jest unit tests for 3 existing components that lack them

## 10.3  PR Expectations

- Every PR must have a screenshot of the component in the PR description

- Every PR must include 'Before' and 'After' screenshots for bug fixes

- Every component must be tested at 375px and 1440px before opening PR

- No PR larger than 200 lines — break large tasks into smaller PRs

- Respond to all review comments within 24 hours

# SECTION 11 — DEVOPS INTERN: COMPLETE ROADMAP

## 11.1  Week 1 — Docker Mastery

- Read: Docker official getting-started guide (https://docs.docker.com/get-started/)

- Run the existing docker-compose.yml and verify all services start

- Understand each service: postgres, redis, backend, celery-worker, frontend, nginx

- Add a new service to docker-compose.yml: pgAdmin (PostgreSQL GUI) on port 5050

- Document the complete service dependency map in a diagram

## 11.2  Week 2 — CI/CD with GitHub Actions

- Read: GitHub Actions documentation (https://docs.github.com/en/actions)

- Understand the existing .github/workflows/ci.yml file

- Add a new GitHub Actions step: run Bandit (Python security linter) on every PR

- Set up automated Slack notification when CI fails

## 11.3  Week 3 — Redis & Celery Monitoring

- Set up Flower (Celery monitoring UI) as a Docker service

- Configure Redis persistence (AOF mode) so queue survives container restart

- Set up Redis memory alerting: alert if Redis memory >75%

- Document how to manually retry failed Celery tasks via Flower

## 11.4  Week 4 — Monitoring Stack

- Add Prometheus metrics endpoint to the FastAPI app (prometheus-fastapi-instrumentator)

- Configure Prometheus to scrape the metrics endpoint every 15 seconds

- Import the FastAPI dashboard into Grafana (dashboard ID: 16110)

- Create an alert: notify Santanu if HTTP error rate >5% for 5 minutes

## 11.5  Environment Variables & Secrets

- Create GitHub Actions Secrets for: DATABASE_URL, REDIS_URL, SECRET_KEY, AWS keys

- Document every environment variable in pdfflow-docs/devops/env-variables.md

- Rotate the staging SECRET_KEY and verify application still works

- Set up Doppler or similar secrets manager for local development

## 11.6  Logging

- Configure structured JSON logging in the FastAPI app using python-json-logger

- Configure Nginx access logs to include response time and upstream address

- Set up log rotation on the production server (logrotate config)

- Create a simple log grep command cheat sheet in the team docs

# SECTION 12 — QA INTERN: COMPLETE ROADMAP

## 12.1  Week 1 — Manual Testing Basics

- Read the product features list (Section 15 of this handbook)

- Set up a local environment following Section 3.3 — you need a working app to test

- Read: What is software testing? (ISTQB Foundation concepts)

- Create your first test case document in the shared Notion: Test Cases > Sprint 1

## 12.2  Test Case Template

Every test case must follow this structure:

| Field | Description |
| --- | --- |
| Test Case ID | TC-TOOL-001 (e.g. TC-MERGE-001) |
| Feature | Merge PDF |
| Precondition | User is logged in. Two valid PDF files are available. |
| Test Steps | 1. Go to /tools/merge-pdf 2. Upload File A 3. Upload File B 4. Click Merge |
| Expected Result | A single merged PDF is downloaded containing all pages from both files in order |
| Actual Result | To be filled during testing |
| Status | Pass / Fail / Blocked |
| Severity (if Fail) | Critical / High / Medium / Low |

## 12.3  Bug Reporting Template

- Title: [Tool Name] [Short description of bug]

- Steps to Reproduce: numbered steps exactly as performed

- Expected Behavior: what should have happened

- Actual Behavior: what actually happened

- Environment: browser, OS, viewport size

- Attachments: screenshot or screen recording (required for UI bugs)

- Severity: Critical (data loss/security) / High (feature broken) / Medium (UX issue) / Low (cosmetic)

## 12.4  Playwright Automation Setup

- Install Playwright: npm install -D @playwright/test && npx playwright install

- Study Harshitha's existing E2E tests in frontend/tests/e2e/

- Write automated tests for the 3 highest-priority tools (Merge, Compress, OCR)

- Add your tests to the CI pipeline — they must pass before any PR can merge

## 12.5  Cross-Browser Testing

- Chrome (latest) — primary browser, test every feature

- Firefox (latest) — test every feature

- Safari 16+ on macOS — test every feature (file input behavior differs)

- Chrome on Android (Pixel 7 or equivalent) — test upload and download flows

- Safari on iOS 16+ (iPhone 14 equivalent) — test upload and download flows

## 12.6  Release Testing Checklist

Before every deployment to production, QA must sign off by completing:

- Full regression test on staging: all 20 tools tested with valid inputs

- Authentication flow: register, login, forgot password, session expiry

- Payment / upgrade flow (when implemented)

- Mobile responsiveness check at 375px on Chrome DevTools

- All Playwright E2E tests passing in CI

- No critical or high severity bugs open in GitHub Issues

- Sign-off message posted in #releases channel: 'QA approved for release vX.X.X'

# SECTION 13 — PARV & SAMRIDDHI: RESEARCH ROADMAP

## 13.1  Research Mission

The Research Team's job is to ensure PDFFlow is built based on evidence, not assumptions. Every design decision, every feature priority, and every UX pattern should be backed by data from your research. You are the user's voice in every product meeting.

## 13.2  Parv — Primary Research Lead

### Responsibilities

- Lead competitor analysis: document every PDF tool with screenshots of their workflows

- Benchmark performance of competitors: time their processing, note file size limits

- User interview coordination: recruit 10 beta users and run structured 30-minute interviews

- Create user personas (minimum 3) with goals, frustrations, and technical skill levels

- Analyze user interview recordings and create insight reports

- Maintain the research repository in Notion with all findings categorized by feature

### Competitor Analysis Template

| Tool | ILovePDF | Smallpdf | Adobe Acrobat Online |
| --- | --- | --- | --- |
| Free file limit |  |  |  |
| Processing speed |  |  |  |
| AI features? |  |  |  |
| Mobile experience |  |  |  |
| Pricing model |  |  |  |
| Developer API? |  |  |  |

## 13.3  Samriddhi — UX & Design Research

### Responsibilities

- Collect UI design references for each tool page — minimum 5 examples per tool

- Create annotated screenshots explaining what works and what does not in competitor UIs

- Propose wireframes for the 5 most complex tool pages (Merge, Split, Sign, OCR, AI Summarise)

- Define the copy (button labels, empty states, error messages) for every tool page

- Maintain the PDFFlow icon and asset library — source or create SVG icons for each tool

- Produce the PDF Flow design brief document that Archita uses as her design reference

## 13.4  Shared Deliverables

| Deliverable | Owner | Due |
| --- | --- | --- |
| Competitor analysis spreadsheet | Parv | End of Week 2 |
| 3 user personas document | Parv | End of Week 3 |
| UI reference library (Figma/Notion) | Samriddhi | End of Week 2 |
| UX copy for all 20 tool pages | Samriddhi | End of Week 4 |
| Feature priority recommendation | Both | End of Week 2 |
| Beta user interview report (10 users) | Parv | Month 3 |
| SVG icon set for all 20 tools | Samriddhi | End of Week 3 |

# SECTION 14 — ARPIT: CONTENT ROADMAP

## 14.1  Content Mission

Arpit is responsible for every word users read in PDFFlow — from the homepage headline to the tooltip on an obscure setting. Good content reduces support requests, improves conversions, and makes the product feel professional and trustworthy.

## 14.2  Content Deliverables

### Phase 1 — Core Product Content

- Homepage: headline, subheadline, hero CTA, tool grid labels, features section, footer

- All 20 tool pages: page title, description, step-by-step instructions, FAQ section (5 questions per tool)

- Auth pages: login, signup, and forgot-password page copy

- Pricing page: plan names, feature list copy, CTA buttons

- Error messages: 404 page, server error page, form validation messages

### Phase 2 — Documentation

- User Guide: How to use each tool (with screenshots from QA team)

- Developer API Guide: authentication, endpoints, request/response examples, rate limits

- FAQ page: 20 most common user questions with clear answers

- Privacy Policy and Terms of Service (template-based, reviewed by Santanu)

### Phase 3 — SEO & Marketing

- Meta titles and descriptions for all 25+ pages

- Long-form blog posts (1,500+ words) for top 5 keyword targets

- Keyword: 'merge PDF free', 'compress PDF online', 'PDF to Word converter', etc.

- Press kit: product description, key facts, founder quotes, feature list

## 14.3  Content Style Guide

- Voice: Direct, helpful, and professional — never corporate-jargon

- Tone: Friendly and competent — like a knowledgeable colleague, not a salesperson

- Headings: Title Case for H1/H2, sentence case for H3 and below

- CTAs: Use action verbs — 'Merge PDF Now', 'Compress for Free', 'Try It Free'

- Error messages: Always tell the user what went wrong AND what to do next

- Avoid: 'please', 'simply', 'just', 'easy', 'seamless' — these are filler words

## 14.4  Collaboration Process

- Arpit writes all copy in a shared Notion page for each section

- Samriddhi reviews for tone and UX alignment

- Santanu reviews for accuracy (especially API docs and technical content)

- Archita or Harshitha implements the copy into the frontend

- QA Intern verifies the live content matches Arpit's approved copy

# SECTION 15 — COMPLETE FEATURE OWNERSHIP MATRIX

This matrix is the single source of truth for who owns what. If there is ever a question about ownership, this table is the answer. Primary Owner is accountable for delivery. Secondary Owner assists. Reviewer approves the PR.

| Feature | Primary | Frontend | Reviewer | Libraries | Est. | Definition of Done |
| --- | --- | --- | --- | --- | --- | --- |
| Merge PDF | Gyan | Archita | Santanu | PyMuPDF | 3 days | Merges 2+ PDFs, output downloadable |
| Split PDF | Gyan | Archita | Santanu | PyMuPDF | 3 days | Splits by page range or count |
| Compress PDF | Gyan | Harshitha | Santanu | pypdf, Ghostscript | 4 days | Reduces file size, maintains readability |
| PDF to JPG | Gyan | Archita | Santanu | pdf2image, Pillow | 3 days | Each page exported as JPG/PNG |
| JPG to PDF | Gyan | Archita | Santanu | PyMuPDF, Pillow | 2 days | Images combined into one PDF |
| Rotate PDF | BE Intern | Harshitha | Gyan | PyMuPDF | 2 days | Pages rotated by specified degrees |
| Add Page Numbers | BE Intern | Archita | Gyan | PyMuPDF | 3 days | Numbers stamped at user-chosen position |
| Word to PDF | Gyan | Harshitha | Santanu | LibreOffice CLI | 3 days | .docx converted to PDF |
| PDF to Word | Gyan | Archita | Santanu | python-docx, PyMuPDF | 5 days | PDF content extracted to .docx |
| Excel to PDF | Gyan | Harshitha | Santanu | LibreOffice CLI | 2 days | .xlsx sheets converted to PDF |
| PDF to Excel | Gyan | Harshitha | Santanu | camelot-py | 5 days | Tables extracted to .xlsx |
| PPT to PDF | BE Intern | Archita | Gyan | LibreOffice CLI | 2 days | .pptx converted to PDF |
| OCR PDF | Gyan | Archita | Santanu | pytesseract, pdf2image | 5 days | Scanned PDF becomes searchable |
| Protect PDF | BE Intern | Harshitha | Gyan | pypdf | 2 days | Password-protected PDF created |
| Unlock PDF | BE Intern | Harshitha | Gyan | pypdf, qpdf | 2 days | Password removed from PDF |
| Watermark PDF | BE Intern | Archita | Gyan | PyMuPDF | 3 days | Text or image watermark on all pages |
| Sign PDF | Gyan | Archita | Santanu | pyhanko | 7 days | Digital signature applied to PDF |
| AI Summarise | Gyan | Archita | Santanu | Anthropic SDK | 5 days | PDF content summarised by AI |
| AI Translate | Gyan | Harshitha | Santanu | Anthropic SDK | 5 days | PDF translated to target language |
| AI Rewrite | Gyan | Harshitha | Santanu | Anthropic SDK | 5 days | PDF content rewritten in target tone |

# SECTION 16 — COMPLETE GIT STRATEGY

## 16.1  Branch Structure

| Branch | Who Uses It | Purpose |
| --- | --- | --- |
| main | Santanu only | Production-ready code. Every commit here is deployed to production. |
| develop | All engineers | Integration branch. All completed features merge here first. |
| feature/* | All engineers | New features, one branch per feature/task |
| bugfix/* | All engineers | Bug fixes for issues found in develop |
| hotfix/* | Santanu, Gyan | Emergency production fixes. Merges into both main and develop. |
| release/* | Santanu only | Release preparation: version bumps, changelogs, final testing. |

## 16.2  Branch Naming Conventions

| Type | Examples |
| --- | --- |
| Backend feature | feature/backend/merge-pdf ¦ feature/backend/auth-jwt |
| Frontend feature | feature/frontend/merge-pdf-page ¦ feature/frontend/upload-zone |
| DevOps feature | feature/devops/prometheus-setup ¦ feature/devops/github-actions |
| Bug fix | bugfix/123-merge-corrupted-output ¦ bugfix/456-mobile-upload |
| Hot fix | hotfix/critical-auth-bypass ¦ hotfix/s3-upload-failure |
| Release | release/v1.0.0 ¦ release/v1.1.0 |

## 16.3  Commit Message Format

Follow Conventional Commits (https://www.conventionalcommits.org). This is enforced by commitlint in the CI pipeline.

type(scope): short description under 72 characters

Types: feat | fix | docs | style | refactor | test | chore | ci

Scopes: backend | frontend | devops | db | api | worker | ui | auth

Examples:

feat(backend): add PDF merge endpoint with multi-file support

fix(frontend): resolve mobile upload zone not triggering on iOS Safari

test(backend): add unit tests for compress worker edge cases

docs(api): update OpenAPI schema for compress endpoint

## 16.4  Pull Request Rules

- PR title must match the commit format: type(scope): description

- PR description must include: What changed, Why it changed, How to test it

- Every PR must reference the GitHub Issue it resolves: 'Closes #123'

- All CI checks must be green before requesting review

- Maximum PR size: 400 lines changed (excluding auto-generated files)

- PRs open >3 days without response will be pinged in Slack by Santanu

## 16.5  GitHub Branch Protection Rules

### main branch

- Require PR before merging (no direct pushes)

- Require 1 approving review (must be Santanu)

- Require all status checks to pass: test, lint, security-scan

- Require branches to be up to date before merging

- Restrict who can push: Santanu only

### develop branch

- Require PR before merging

- Require 1 approving review

- Require all status checks to pass

- Can be merged by: Santanu, Gyan (backend PRs), Archita (frontend PRs)

# SECTION 17 — COMPLETE FOLDER OWNERSHIP

This section is your map. If you are unsure which file to edit, find it in this list to confirm you are in the right place. If your task requires modifying a folder owned by someone else, communicate with them first.

| Path | Owner(s) | Description |
| --- | --- | --- |
| backend/app/main.py | Santanu | FastAPI app initialization, middleware setup |
| backend/app/core/ | Santanu | Config, security, database connection factory |
| backend/app/api/v1/endpoints/ | Gyan + BE Intern | All API route handlers, one file per tool |
| backend/app/api/v1/router.py | Santanu | API router that includes all endpoint routers |
| backend/app/models/ | Gyan | SQLAlchemy ORM models |
| backend/app/schemas/ | Gyan | Pydantic request/response schemas |
| backend/app/services/ | Gyan | Business logic layer (auth, file handling, job management) |
| backend/app/workers/ | Gyan + BE Intern | Celery task functions, one file per tool |
| backend/app/celery_app.py | Santanu | Celery app configuration and initialization |
| backend/alembic/ | Gyan + Santanu | Database migrations |
| backend/tests/ | Gyan + BE Intern | All pytest test files |
| backend/requirements.txt | Santanu | Production Python dependencies |
| backend/Dockerfile | DevOps Intern + Santanu | Backend Docker image definition |
| frontend/app/ | Archita (pages), Harshitha (integrations) | Next.js App Router pages and layouts |
| frontend/app/(tools)/[tool]/ | Archita | Dynamic tool page template |
| frontend/app/(auth)/ | Archita | Login, signup, forgot-password pages |
| frontend/app/(dashboard)/ | Archita + Harshitha | Dashboard, history, settings pages |
| frontend/components/ui/ | Archita + FE Intern | Shared design system components |
| frontend/components/tools/ | Archita | Tool-specific components (PageSelector, OptionPanel) |
| frontend/components/layout/ | Harshitha | Header, Footer, Sidebar, Navigation |
| frontend/lib/api/ | Harshitha | API client functions |
| frontend/lib/hooks/ | Archita + Harshitha | Custom React hooks |
| frontend/lib/store/ | Archita | Zustand store definitions |
| frontend/lib/utils/ | Anyone | Pure utility functions |
| frontend/tests/e2e/ | Harshitha + QA Intern | Playwright E2E tests |
| frontend/stories/ | Archita + FE Intern | Storybook stories |
| frontend/public/icons/ | Samriddhi | Tool SVG icons |
| docker-compose.yml | DevOps Intern + Santanu | Local development services |
| docker-compose.prod.yml | Santanu | Production overrides |
| .github/workflows/ | DevOps Intern + Santanu | GitHub Actions CI/CD pipelines |
| nginx/ | DevOps Intern | Nginx configuration for reverse proxy |
| monitoring/ | DevOps Intern | Prometheus config, Grafana dashboard JSON |

# SECTION 18 — PHASE-WISE EXECUTION PLAN

## 18.1  Phase 1 — Foundation (Weeks 1–6)

### Goals

- Development environment standardized across all members

- Core infrastructure (auth, file upload, job queue) working

- First 10 tools built and tested on staging

- CI/CD pipeline running with automated tests

| Week | Focus | Owners | Deliverables |
| --- | --- | --- | --- |
| 1 | Environment & Architecture | Santanu (lead), All | All environments working, repos created, team kickoff done |
| 2 | Auth + File Upload Backend | Gyan, Santanu | Auth endpoints live, S3 upload working, DB migrations run |
| 3 | Core UI + Design System | Archita, FE Intern | Component library started, homepage design live on localhost |
| 4 | Tools 1-5 (Backend) | Gyan, BE Intern | Merge, Split, Compress, PDF-to-JPG, JPG-to-PDF workers complete |
| 5 | Tools 1-5 (Frontend) | Archita, Harshitha | First 5 tool pages connected to backend API on staging |
| 6 | Tools 6-10 + QA Round 1 | Gyan, Archita, QA Intern | Tools 6-10 complete, first QA regression cycle done |

## 18.2  Phase 2 — Growth (Weeks 7–12)

### Goals

- All 20 tools live and tested

- Public beta launched with real users

- Developer API v1 released

- Performance targets met (<3s processing for files under 10MB)

| Week | Focus | Owners | Deliverables |
| --- | --- | --- | --- |
| 7 | Tools 11-15 (Backend) | Gyan, BE Intern | Word/Excel/PPT conversions and OCR working |
| 8 | Tools 11-15 (Frontend) | Harshitha, FE Intern | Conversion tool pages live |
| 9 | AI Tools + Sign PDF | Gyan (AI), Archita (UI) | Summarise, Translate, Rewrite, Sign PDF complete |
| 10 | Performance + Optimization | Santanu, Gyan, Harshitha | Load testing done, bottlenecks fixed |
| 11 | Staging Final QA | QA Intern, All | All 20 tools passing QA, regression suite passing |
| 12 | Public Beta Launch | Santanu (leads), All | Production deployment, monitoring active, users onboarded |

## 18.3  Phase 3 — Scale (Months 4–6)

- Feedback from public beta incorporated into backlog

- Mobile apps development begins (React Native)

- Auto-scaling infrastructure implemented

- B2B / enterprise plan developed

- Team scaling: hiring 4-5 additional engineers

# SECTION 19 — DAILY DEVELOPMENT LIFECYCLE

## 19.1  The Standard Developer Day

| Time | Activity |
| --- | --- |
| 09:00 | Async standup in Slack: What did I complete yesterday? What am I doing today? Any blockers? |
| 09:15 | Pull latest from develop: git pull origin develop |
| 09:20 | Check your assigned GitHub Issues and pick the highest-priority open task |
| 09:30–13:00 | Deep work: code, test, iterate |
| 13:00–14:00 | Lunch / break |
| 14:00–17:30 | Continue development; respond to PR review comments |
| 17:30 | Push your branch and open/update your PR if ready for review |
| 17:45 | Update your GitHub Issue with progress comment |

## 19.2  The Complete Task Lifecycle

- PICK TASK — Assign yourself the GitHub Issue. Move it to 'In Progress' on the project board

- CREATE BRANCH — git checkout develop && git pull origin develop && git checkout -b feature/backend/my-task-name

- WRITE CODE — Follow the patterns in existing code. Ask questions early, not after 4 hours

- WRITE TESTS — Every new function needs a test. Run pytest locally: pytest tests/ -v

- COMMIT — git add -p (stage hunks interactively) && git commit -m 'feat(backend): short description'

- PUSH — git push origin feature/backend/my-task-name

- OPEN PR — Use the PR template. Link the issue. Add screenshots for UI changes

- REVIEW — Address all comments within 24 hours. Mark conversations 'Resolved' after fixing

- APPROVAL — PR is approved by designated reviewer (see Section 2.2)

- MERGE — Squash merge to develop. Delete the feature branch after merge

- DEPLOY — DevOps Intern / Santanu triggers deployment to staging via GitHub Actions

- VERIFY — Test your feature on staging. Check monitoring for errors

- CLOSE ISSUE — Move the GitHub Issue to 'Done'. Leave a comment confirming it is live on staging

## 19.3  Weekly Team Rhythm

| Day | Meeting | Who Attends |
| --- | --- | --- |
| Monday 10:00 | Sprint Planning (30 min) | All engineers + Santanu |
| Wednesday 11:00 | Mid-sprint check-in (15 min) | All engineers + Santanu |
| Friday 17:00 | Sprint Review / Demo (45 min) | Full team including Research + Content |
| Friday 17:45 | Retrospective (30 min) | All engineers + Santanu |

## 19.4  Hotfix Process

A hotfix is only for critical production issues: data loss, security vulnerabilities, or complete feature failure affecting >50% of users.

- Santanu declares a hotfix and creates: git checkout main && git checkout -b hotfix/short-description

- Gyan (backend) or Archita (frontend) immediately begins the fix

- No feature additions during a hotfix — only the minimum code to fix the issue

- Tests written and passing before opening the hotfix PR

- Santanu reviews and merges hotfix to main AND develop

- Immediate deployment to production

- Post-mortem document written within 48 hours: what failed, why, how to prevent it

# SECTION 20 — TEAM SCALING PLAN

## 20.1  Current State — 11 Members

The current team is a lean, full-stack crew. Everyone wears multiple hats. Santanu reviews all backend and architecture. Gyan leads backend delivery. Archita and Harshitha share the frontend.

## 20.2  At 15 Members — Adding Depth

### New Hires Recommended

- 1x Senior Backend Engineer — takes ownership of AI tools, reduces Santanu's review load

- 1x Frontend Engineer — takes Harshitha's E2E testing load, allows Harshitha to focus on integrations

- 1x QA Engineer (not intern) — leads QA Intern, owns the automation suite

- 1x DevOps Engineer (not intern) — owns infrastructure, Santanu steps back from DevOps

### Process Changes

- Introduce backend code owners file: Senior Backend Engineer reviews Gyan's PRs, Santanu only reviews architecture

- Split sprint planning: Backend sprint (Monday AM) + Frontend sprint (Monday PM)

- Dedicated design review meeting: Research team presents mockups every 2 weeks

## 20.3  At 25 Members — Building Squads

### Recommended Squad Structure

| Squad | Focus | Members |
| --- | --- | --- |
| Core Tools Squad | PDF manipulation tools | 2 Backend, 2 Frontend, 1 QA |
| AI Squad | AI features, ML pipeline | 1 Senior Backend, 1 ML Engineer, 1 Frontend |
| Platform Squad | API, auth, billing, DevOps | 1 Senior Backend, 1 DevOps, 1 Frontend |
| Growth Squad | SEO, landing pages, content | 1 Frontend, 1 Content, 1 UX Researcher |

### New Roles Needed at 25

- Engineering Manager (Santanu transitions from coding to managing)

- Product Manager — owns the roadmap and user research

- ML Engineer — owns AI model fine-tuning and prompt engineering

- Security Engineer — owns OWASP compliance, penetration testing

## 20.4  At 50 Members — Scaling Organizational Design

- Multiple Engineering Managers, each owning one squad cluster

- VP of Engineering hired — Santanu becomes CTO

- Platform Engineering team: Kubernetes, service mesh, internal developer platform

- Data Engineering team: analytics pipeline, user behavior tracking, A/B testing infrastructure

- Customer Success team: handles enterprise B2B relationships

- Release cadence: bi-weekly releases with dedicated release manager per cycle

- Architecture Review Board: Santanu + 2 senior engineers approve all major technical decisions

# SECTION 21 — FINAL PROJECT CHECKLIST

This is the master checklist for project completion. Every item must be checked off before PDFFlow can be declared production-ready. Santanu is responsible for verifying every item. Nothing ships until this list is complete.

## 21.1  Infrastructure & DevOps

### Repositories

- [ ]  pdfflow-app repository created and all team members have appropriate access

- [ ]  pdfflow-infra repository created with Docker and Nginx configs

- [ ]  pdfflow-docs repository created with initial structure

- [ ]  Branch protection rules configured on main and develop

- [ ]  CODEOWNERS file created mapping folders to reviewers

### CI/CD Pipeline

- [ ]  GitHub Actions workflow runs on every PR: lint, test, type-check

- [ ]  Security scanning (Bandit for Python, npm audit for Node) runs in CI

- [ ]  Automated deployment to staging on every merge to develop

- [ ]  Manual production deployment workflow requiring Santanu approval

- [ ]  Playwright E2E tests run in CI against staging before production release

### Infrastructure

- [ ]  Docker Compose file runs all services cleanly from a fresh clone

- [ ]  Production server provisioned and hardened

- [ ]  SSL certificates configured and auto-renewing (Let's Encrypt)

- [ ]  Nginx configured as reverse proxy with rate limiting

- [ ]  PostgreSQL backup configured (daily automated, 30-day retention)

- [ ]  Redis persistence configured (AOF mode)

- [ ]  S3/R2 bucket created with lifecycle rules (delete files after 60 minutes)

## 21.2  Backend

### Core Systems

- [ ]  FastAPI application starts without errors

- [ ]  Database migrations are up to date (alembic upgrade head runs clean)

- [ ]  JWT authentication working (register, login, refresh, logout)

- [ ]  File upload endpoint working with S3 integration

- [ ]  Job queue (Celery + Redis) processing tasks successfully

- [ ]  Job status polling endpoint returning accurate progress

- [ ]  File download endpoint generating valid presigned URLs

### All 20 Tools

- [ ]  Merge PDF — worker and API complete and tested

- [ ]  Split PDF — worker and API complete and tested

- [ ]  Compress PDF — worker and API complete and tested

- [ ]  PDF to JPG — worker and API complete and tested

- [ ]  JPG to PDF — worker and API complete and tested

- [ ]  Rotate PDF — worker and API complete and tested

- [ ]  Add Page Numbers — worker and API complete and tested

- [ ]  Word to PDF — worker and API complete and tested

- [ ]  PDF to Word — worker and API complete and tested

- [ ]  Excel to PDF — worker and API complete and tested

- [ ]  PDF to Excel — worker and API complete and tested

- [ ]  PPT to PDF — worker and API complete and tested

- [ ]  OCR PDF — worker and API complete and tested

- [ ]  Protect PDF — worker and API complete and tested

- [ ]  Unlock PDF — worker and API complete and tested

- [ ]  Watermark PDF — worker and API complete and tested

- [ ]  Sign PDF — worker and API complete and tested

- [ ]  AI Summarise — worker and API complete and tested

- [ ]  AI Translate — worker and API complete and tested

- [ ]  AI Rewrite — worker and API complete and tested

### Quality

- [ ]  Backend test coverage >80% (pytest --cov report)

- [ ]  All tests passing in CI pipeline

- [ ]  OpenAPI documentation up to date for all endpoints

- [ ]  Performance tested: <3s processing at 95th percentile for <10MB files

- [ ]  Rate limiting implemented and tested

- [ ]  Error handling returns consistent JSON error responses

## 21.3  Frontend

### Core Pages

- [ ]  Homepage with full tool grid is live and responsive

- [ ]  All 20 tool pages are functional (upload, process, download works end-to-end)

- [ ]  Login page works with correct credentials and rejects wrong credentials

- [ ]  Signup page creates account and sends verification email

- [ ]  Dashboard shows job history correctly

- [ ]  Pricing page shows free vs pro comparison

- [ ]  404 page is friendly and has working navigation links

### Quality

- [ ]  Lighthouse score >85 on Homepage and 5 most-used tool pages

- [ ]  No console errors in Chrome DevTools on any page

- [ ]  All components have Jest tests

- [ ]  All shared components documented in Storybook

- [ ]  WCAG 2.1 AA automated audit passes (axe DevTools)

- [ ]  No layout breakages at 320px, 768px, 1024px, 1440px

## 21.4  QA & Testing

### Manual Testing

- [ ]  All 20 tools manually tested on Chrome, Firefox, Safari

- [ ]  All critical flows tested on mobile (375px Chrome + Safari iOS)

- [ ]  Authentication flows tested: happy path + all error states

- [ ]  File validation tested: wrong types, oversized files, corrupted PDFs

- [ ]  No critical or high severity bugs open in GitHub Issues

### Automation

- [ ]  Playwright E2E tests passing for all critical user journeys

- [ ]  E2E tests running in CI pipeline

- [ ]  All backend unit tests passing

## 21.5  Content & Documentation

### Product Content

- [ ]  Homepage copy written, reviewed, and implemented

- [ ]  All 20 tool page descriptions written and implemented

- [ ]  All UI error messages written (specific, actionable, not technical jargon)

- [ ]  All empty states written (dashboard empty, no jobs yet, etc.)

- [ ]  Pricing page copy written and implemented

### Technical Documentation

- [ ]  API documentation live at /docs (Swagger) and /redoc

- [ ]  Developer guide published in pdfflow-docs

- [ ]  README.md in pdfflow-app repo is accurate and complete

- [ ]  Deployment runbook written in pdfflow-docs/devops/

- [ ]  Post-mortem template created in pdfflow-docs/incidents/

## 21.6  Monitoring & Operations

### Monitoring

- [ ]  Prometheus collecting metrics from backend

- [ ]  Grafana dashboard shows: request rate, error rate, job queue depth, processing time

- [ ]  Alert configured: HTTP error rate >5% for 5 minutes notifies Santanu via Slack

- [ ]  Alert configured: Celery queue depth >100 jobs notifies Santanu

- [ ]  Alert configured: Database connection failures notify Santanu immediately

- [ ]  Sentry configured and receiving errors from both backend and frontend

### Operations

- [ ]  On-call rotation defined (Santanu primary, Gyan secondary)

- [ ]  Rollback procedure documented and tested on staging

- [ ]  Database restore drill completed successfully

- [ ]  Incident response guide written

## 21.7  Go-Live Sign-Off

### Final Sign-Offs

- [ ]  Santanu: Architecture and backend reviewed and approved

- [ ]  Gyan: All backend tools tested and confirmed working

- [ ]  Archita: All frontend pages reviewed and confirmed working

- [ ]  Harshitha: All API integrations and E2E tests passing

- [ ]  QA Intern: Regression test complete, sign-off comment posted in #releases

- [ ]  Arpit: All live content reviewed and approved

- [ ]  DevOps Intern: All monitoring and alerting verified working

- [ ]  DNS cutover plan written and reviewed by Santanu

- [ ]  Go-live date confirmed with all stakeholders

END OF PDFFLOW ENGINEERING EXECUTION HANDBOOK

Version 1.0 — Prepared for the PDFFlow Team

This document is the single source of truth for the PDFFlow project. Questions? Ask Santanu.